## Tasks
id | name | duration | resources | predecessors | description | asap_start | asap_finish | alap_start | alap_finish | scheduled_start | scheduled_finish | on_critical_chain | original_duration | ccpm_duration | safety_removed | execution_status | actual_start | actual_finish | linked_task | delivery_date
CC1 | Critical 1 | 5 | R1 |  |  | 0 | 4 | 296 | 300 | 296 | 300 | FALSE | 10 | 5 | 5 | NOT_STARTED
CC2 | Critical 2 | 7 | R1 | FC1B,FeedingBuffer-CC2 |  | 9 | 17 | 305 | 311 | 305 | 311 | TRUE | 15 | 7 | 8 | NOT_STARTED
CC3 | Critical 3 | 5 | R1 | CC2,FeedingBuffer-CC3 |  | 18 | 24 | 315 | 319 | 315 | 319 | TRUE | 10 | 5 | 5 | NOT_STARTED
FC1A | Feed 1A | 4 | R2 |  |  | 0 | 3 | 296 | 299 | 296 | 299 | TRUE | 8 | 4 | 4 | NOT_STARTED
FC1B | Feed 1B | 3 | R2 | FC1A |  | 4 | 8 | 301 | 303 | 301 | 303 | TRUE | 7 | 3 | 4 | NOT_STARTED
FC2A | Feed 2A | 3 | R3 |  |  | 0 | 2 | 301 | 303 | 301 | 303 | FALSE | 6 | 3 | 3 | NOT_STARTED
FC2B | Feed 2B | 4 | R3 | FC2A |  | 3 | 8 | 305 | 308 | 305 | 308 | FALSE | 9 | 4 | 5 | NOT_STARTED
FeedingBuffer-CC2 | Feeding Buffer for CC2 | 2 |  | CC1 |  | 7 | 8 | 302 | 303 | 302 | 303 | FALSE |  |  | 0 | NOT_STARTED |  |  | CC2
FeedingBuffer-CC3 | Feeding Buffer for CC3 | 4 |  | FC2B |  | 9 | 14 | 310 | 313 | 310 | 313 | FALSE |  |  | 0 | NOT_STARTED |  |  | CC3
ProjectBuffer | Project Buffer | 10 |  | CC3 |  | 25 | 38 | 353 | 362 | 353 | 362 | FALSE |  |  | 0 | NOT_STARTED

## Resources
id | name | non_working_days | capacity_per_day
R1 | Core Team | [] | 1
R2 | Team A | [20, 21] | 1
R3 | Team B | [30, 31] | 1

## ProjectCalendar
non_working_days
5
6
12
13
19
20
26
27
33
34
40
41
47
48
54
55